## Sheet1
Test Number | System | Test/Task | expected redult | Result (pass/fail) | Comment
1 | None | Ask important questions from testing tickets (5623 and 5462)
2 | SECI | Record all motor position and block values in SECI |  | PASS
3 | None | Install | installed with config | PASS
4 | IBEX | Motor Setup: set ioc to dev sim and IP to nothing, set autosave in dev sim (ln galil st.common lines 105.m 108), run motor setup script script (wait at least 30s) | autosave is written | PASS
5 | IBEX | Put motors in not rec sim and set ip addreses. Check connection | Motors are connected and give same positions as in seci | PASS
6 | IBEX | Record motor positions in IBEX | screen shot saved | PASS
7 | SECI | Swap to SECI by using stop_ibex_server_start_seci.bat | SECI is started and DAE works | PASS
8 | SECI | Check motor positions | Motor positions are as in SECI originally and IBEX | PASS
9 | SECI | POLREF: Move bench to multiple positions (theta and sm) record motor position | Motor positions recorded for sm and angle
10 | SECI | INTER: Move multiple mirrors to multiple positions record motor position | Motor positions recorded for sm1 and sm2 | -
11 | SECI | Move all motors | motors move | PASS
12 | SECI | Record Motor posititions | screen shot saved | PASS | Current sheet is weird. Not move SS Fine or slit 4
13 | IBEX | Swap to IBEX compare motor positions | All motor positions are same | PASS
14 | IBEX | 1. For each of the following motors check. Motor moves up is positive, angle: beam going from right to left +ve rotation is clockwise (or anti clockwise about x). Trans +ve is left in beam direction. Slits +ve going out from centre. PSI - +ve anti-clockwise about z CHI - +ve anti-clockwise when lookin along y (up). 2. Backlash in correct direction (e.g. from above move past sp and back, angle is weird) 3. Energised or not (Should be energised if there is a green light in SECI *#??) 4. Limits | motor moves in correct direction, backlash good, energise, limits |  | We did not check limits because of time limits
15 | IBEX | MOT0101 |  | - | Can not see so can not check
16 | IBEX | MOT0102 |  | - | Can not see so can not check
17 | IBEX | MOT0103 |  | - | Can not see so can not check
18 | IBEX | MOT0104 |  | - | Can not see so can not check
19 | IBEX | MOT0105 |  | PASS
20 | IBEX | MOT0106 |  | PASS
21 | IBEX | MOT0107 |  | PASS | Dir inverted
22 | IBEX | MOT0108 |  | PASS | High/low limit swapped (70, -10 -> -10, 70 don't know how these worked in SECI)
23 | IBEX | MOT0201 |  | PASS
24 | IBEX | MOT0202 |  | PASS
25 | IBEX | MOT0203 |  | PASS
26 | IBEX | MOT0204 |  | PASS
27 | IBEX | MOT0205 |  | PASS
28 | IBEX | MOT0206 |  | PASS
29 | IBEX | MOT0207 |  | PASS | Inverted
30 | IBEX | MOT0208 |  | PASS
31 | IBEX | MOT0301 |  | PASS
32 | IBEX | MOT0302 |  | PASS
33 | IBEX | MOT0303 |  | PASS | Inverted
34 | IBEX | MOT0304 |  | PASS
35 | IBEX | MOT0305 |  | PASS
36 | IBEX | MOT0306 |  | PASS
37 | IBEX | MOT0307 |  | PASS
38 | IBEX | MOT0308 |  | PASS
39 | IBEX | MOT0401 |  | PASS
40 | IBEX | MOT0402 |  | PASS
41 | IBEX | MOT0403 |  | PASS
42 | IBEX | MOT0404 |  | PASS
43 | IBEX | MOT0405 |  | PASS
44 | IBEX | MOT0406 |  | PASS
45 | IBEX | MOT0407 |  | PASS | reduce backlash distance
46 | IBEX | MOT0408 |  | PASS
47 | IBEX | MOT0501 |  |  | Not connected
48 | IBEX | MOT0502 |  |  | Not connected
49 | IBEX | MOT0503 |  | PASS
50 | IBEX | MOT0504 |  | PASS
51 | IBEX | MOT0505 |  |  | Not connected
52 | IBEX | MOT0506 |  |  | Not connected
53 | IBEX | MOT0507 |  |  | Not connected
54 | IBEX | MOT0508 |  |  | Not connected
55 | IBEX | MOT0601 |  | PASS
56 | IBEX | MOT0602 |  | PASS
57 | IBEX | MOT0603 |  | PASS
58 | IBEX | MOT0604 |  | PASS
59 | IBEX | MOT0605 |  | PASS
60 | IBEX | MOT0606 |  | PASS
61 | IBEX | MOT0607 |  | PASS | inverted
62 | IBEX | MOT0608 |  | PASS
63 | IBEX | MOT0701 |  | PASS | backlash added
64 | IBEX | MOT0702 |  | PASS | inverted
65 | IBEX | MOT0703 |  | PASS | backlash added
66 | IBEX | MOT0704 |  | PASS | inverted, backlash added
67 | IBEX | MOT0705 |  | PASS | backlash added
68 | IBEX | MOT0706 |  | PASS | inverted, backlash added
69 | IBEX | MOT0707 |  | PASS | backlash added
70 | IBEX | MOT0708 |  | PASS | inverted, backlash added
71 | IBEX | MOT0801 |  | PASS
72 | IBEX | MOT0802 |  | PASS
73 | IBEX | MOT0803 |  | PASS | inverted
74 | IBEX | MOT0804 |  | PASS
75 | IBEX | MOT0805 |  | -
76 | IBEX | MOT0806 |  | -
77 | IBEX | MOT0807 |  | -
78 | IBEX | MOT0808 |  | -
79 | IBEX | MOT0904 |  | FAIL | Dual stage, ibex doesn’t understand this.
80 | IBEX | Check multiple positions against SECI (sm1 or bench) | Positions are the same | PASS | But used Christy's bench movement spreadsheet not SECI
81 | IBEX | Set everything to straight through beam. Move to laser condition (MONITOR out of the way) | Record what laser mode means (check it is monitor3) | - | No time but axis moves correctly
82 | IBEX | Check tracking | Laser should hit detector mid pixel | PASS
83 | IBEX | Check theta at (0.1, 0.2, 2) | Laser should hit detector mid pixel | PASS | Various points common for POLREF
84 | IBEX | Set super mirror to (0.1) and theta to (0, 0.1, 0.2, 2) [INTER we can't park SM2 set offset to #) | Laser should hit detector mid pixel | PASS | Various points common for POLREF
85 | IBEX | Set super mirror to (0.5) and theta to (0, 0.1, 0.2, 2) |  | PASS | Various points common for POLREF
86 | IBEX | INTER: repeat above second mirror |  | -
87 | IBEX | INTER: do both mirrors |  | -